## Project Overview
IAM-Secure-Gate: Intelligent IAM Misconfiguration Auditor & Remediation Pipeline
Project Information
Student: | Roko Skugor
Supervisor: | Dariusz Terefenko
Programme: | TU865
Repository: | https://github.com/steins-r-gate/IaC-Secure-Gate
Duration: | 20 weeks (5 phases x 4 weeks)
Budget: | <€15/month
Current Spend: | €2.72/month (KMS €0.90 + S3 €0.02 + CloudTrail €1.80)
Problem: | 68% of breaches involve IAM misconfigurations (Verizon DBIR 2024)
Solution: | Automated closed-loop security: prevent + detect + remediate
Status: | Phase 1 - Week 3 (Detection Baseline ~35% complete)
5 Core Objectives
Obj 1: | AWS-native detection baseline (CloudTrail, Config, IAM Analyzer, Security Hub) - MTTD <5min
Obj 2: | Automated remediation via EventBridge→Lambda for 3+ IAM issues with approval workflow
Obj 3: | Shift-left IaC security gate blocking PRs with Checkov/OPA integration
Obj 4: | Feedback loop auto-generating OPA policies from runtime findings
Obj 5: | Dashboards and documentation pack for MTTD/MTTR, compliance trends, and system health
Phase Summary
Phase | Weeks | Status | Progress | Milestone | Key Deliverables
Phase 1: AWS Detection Baseline | 1-4 | In Progress | 45% | Week 4: Detection Baseline Complete | KMS ✓, S3 ✓, CloudTrail ✓ ¦ Remaining: Config, IAM Analyzer, Security Hub
Phase 2: Basic Remediation | 5-8 | Not Started | 0% | Week 8: Automated Remediation Live | Lambda functions, EventBridge, SNS approval, MTTR <5min
Phase 3: IaC Security Gate | 9-12 | Not Started | 0% | Week 12: PR Gate Operational | GitHub Actions, Checkov/OPA, PR blocking, SARIF
Phase 4: Metrics & Feedback Loop | 13-16 | Not Started | 0% | Week 16: Closed-Loop System | Grafana dashboards, OPA policy auto-gen, 30-day trends
Phase 5: Visualization & Documentation | 17-20 | Not Started | 0% | Reporting & Docs Complete | Dashboards, reporting pack, runbooks, diagrams, final report & presentation

## Phase 1 - Detection
Phase 1: AWS Detection Baseline (Weeks 1-4)
Task ID | Task Name | Description | Requirements | Status | Dependencies | Est Hours | Notes
CURRENT PROGRESS: 45% Complete (3/8 tasks done)
✅ DEPLOYED: KMS Key + 2 S3 Buckets (CloudTrail & Config) + CloudTrail Multi-Region
🔄 NEXT STEPS: Deploy AWS Config (recorder + 5 rules) → IAM Access Analyzer → Security Hub → Testing
1.1 | AWS Account Setup & Security Hardening | Secure root account, enable MFA, configure billing alerts at €5/€10/€14 | AWS account access, payment method configured | Complete |  | 2 | Root account secured, MFA enabled, billing alerts configured
1.2 | Enable CloudTrail (Multi-region) | Enable CloudTrail across all regions capturing management events, configure encryption with KMS | Understanding of CloudTrail event types, multi-region configuration | Complete | 1.1 | 3 | DEPLOYED: Multi-region CloudTrail capturing IAM events, encrypted with KMS
1.3 | Configure AWS Config Rules (5+ rules) | Enable AWS Config and deploy 5+ managed rules for IAM compliance checking | AWS Config concepts, CIS AWS Foundations Benchmark knowledge | Not Started | 1.2 | 6 | S3 bucket ready ✓ ¦ Need: Config recorder, delivery channel, IAM role, 5+ rules
1.4 | Setup IAM Access Analyzer | Enable IAM Access Analyzer to detect external access to resources | Understanding of resource-based policies, cross-account access | Not Started | 1.1 | 2 | Next priority after Config
1.5 | Enable Security Hub & Integrations | Enable Security Hub, integrate with Config and IAM Analyzer, enable CIS benchmark | Security Hub concepts, security standards enablement | Not Started | 1.3, 1.4 | 4 | Deploy after Config and IAM Analyzer for integration
1.6 | Configure S3 Buckets for Logs | Create S3 buckets with encryption, versioning, lifecycle policies for cost optimization | S3 security best practices, lifecycle policy design | Complete | 1.1 | 3 | DEPLOYED: 2 buckets (CloudTrail + Config) with encryption, versioning, lifecycle policies, 4-layer public access blocking
1.7 | Initial Testing (3 scenarios) | Test detection with 3 attack scenarios: wildcard policy, MFA disable, external access | Ability to trigger test events, verify detection timing | Not Started | 1.5 | 4 | Awaiting Security Hub deployment
1.8 | Document Detection Infrastructure | Create comprehensive documentation with architecture diagrams, configuration details | Technical writing, diagram tools (draw.io), Markdown | In Progress | 1.7 | 5 | Have: PHASE1.md, foundation-documentation.md ¦ Need: Complete README, architecture diagrams

## Phase 2 - Remediation
Phase 2: Basic Remediation (Weeks 5-8)
Task ID | Task Name | Description | Requirements | Status | Dependencies | Est Hours | Notes
2.1 | Design Lambda Remediation Architecture | Design event-driven architecture: Security Hub → EventBridge → Lambda → SNS approval | Event-driven patterns, Lambda best practices, error handling design | Not Started | 1.8 | 4 | Foundation for all remediation functions
2.2 | Create DynamoDB State Tracking Table | Create DynamoDB table to track remediation state, approval status, and audit trail | DynamoDB design, partition key selection, TTL configuration | Not Started | 2.1 | 2 | Enables tracking of remediation actions and approvals
2.3 | Develop Lambda: Wildcard Policy Remediator | Python Lambda to detect and remove wildcard (*) IAM policies automatically | Python, boto3, IAM policy manipulation, Lambda development | Not Started | 2.1 | 8 | First critical remediation - addresses major security risk
2.4 | Develop Lambda: Overpermissive Role Handler | Lambda to identify and restrict overly permissive IAM roles (Admin-like access) | IAM policy analysis, risk scoring logic, Python development | Not Started | 2.1 | 8 | Requires careful logic to avoid breaking legitimate admin roles
2.5 | Develop Lambda: Unrotated Keys Detector | Lambda to detect and disable IAM access keys older than 90 days | IAM access key management, key rotation policies | Not Started | 2.1 | 6 | CIS benchmark requirement - rotate keys every 90 days
2.6 | Configure EventBridge Rules (5+ patterns) | Create EventBridge rules to route specific Security Hub findings to correct Lambda | EventBridge event patterns, filtering logic, target configuration | Not Started | 2.3, 2.4, 2.5 | 4 | Intelligent routing based on finding type and severity
2.7 | Setup SNS Approval Workflow | Create SNS topic for human approval of high-impact remediations | SNS configuration, email subscriptions, approval token handling | Not Started | 2.6 | 3 | Safety mechanism for changes requiring human judgment
2.8 | Lambda Unit & Integration Testing | Develop comprehensive tests for all Lambda functions with mocked AWS services | pytest, moto for AWS mocking, test scenario design | Not Started | 2.7 | 8 | Critical for preventing accidental production damage
2.9 | Measure MTTR (<5min validation) | Execute test scenarios and measure Mean Time To Remediate against target | Timing measurement, metric collection, validation criteria | Not Started | 2.8 | 3 | Validate meets <5min MTTR objective

## Phase 3 - IaC Gate
Phase 3: IaC Security Gate (Weeks 9-12) - SHIFT-LEFT PREVENTION
Task ID | Task Name | Description | Requirements | Status | Dependencies | Est Hours | Notes
3.1 | OPA/Rego Learning & Experimentation | Learn OPA policy language (Rego), experiment with policy writing and testing | Time for learning new technology, OPA documentation study | Not Started |  | 8 | Started early (Week 7) to address learning curve - key risk mitigation
3.2 | Setup GitHub Repository Structure | Organize repo with .github/workflows/, policies/, terraform/, docs/ structure | GitHub Actions knowledge, repo organization best practices | Not Started |  | 2 | Clean separation of IaC, policies, and automation
3.3 | Configure Checkov in GitHub Actions | Create workflow to run Checkov (750+ policies) on every PR with Terraform changes | GitHub Actions syntax, Checkov CLI usage, workflow triggers | Not Started | 3.2 | 4 | First line of defense - comprehensive policy checking
3.4 | Write Custom OPA Policies (3-5 policies) | Write custom Rego policies for IAM-specific violations not covered by Checkov | Rego syntax mastery, IAM policy analysis skills | Not Started | 3.1 | 10 | Examples: wildcard policies, overly permissive assume roles
3.5 | Integrate Conftest into Workflow | Add Conftest to GitHub Actions to evaluate Terraform plans against OPA policies | Conftest usage, Terraform plan JSON parsing, integration | Not Started | 3.4 | 4 | Evaluates planned changes before apply
3.6 | Implement PR Blocking Logic | Configure workflow to block PR merge if critical violations found | GitHub branch protection rules, workflow status checks | Not Started | 3.5 | 3 | Enforces security gate - cannot merge unsafe code
3.7 | Add SARIF Artifact Generation | Generate SARIF format output for GitHub Security tab integration | SARIF format understanding, GitHub Code Scanning integration | Not Started | 3.6 | 3 | Rich UI for reviewing security findings in GitHub
3.8 | BridgeCrew API Integration | Integrate with BridgeCrew API for additional severity scoring and insights | API integration, authentication, rate limit handling | Not Started | 3.7 | 4 | Leverages commercial threat intelligence - free tier
3.9 | Test PR Gate (Block/Approve scenarios) | Create test PRs with intentional violations to validate blocking works correctly | Test scenario design, validation of block/approve logic | Not Started | 3.8 | 5 | Prove the gate works as designed before relying on it

## Phase 4 - Metrics Loop
Phase 4: Metrics Instrumentation & Feedback Loop (Weeks 13-16) - AUTOMATION
Task ID | Task Name | Description | Requirements | Status | Dependencies | Est Hours | Notes
4.1 | Instrument Metrics (MTTD/MTTR, Coverage, Cost) | Add instrumentation to detection/compliance pipeline to emit core KPIs (MTTD/MTTR, coverage %, cost) into a metrics store. | Defined metric names/units, emitted events, initial sanity checks | Not Started |  | 5 | Prefer CloudWatch Metrics/Logs first; keep schema stable for Phase 5 dashboards
4.2 | Normalize Events into Metrics Dataset | Create normalization step to convert raw findings/events into a clean dataset (daily aggregates, per-rule compliance, top findings). | Normalization logic + scheduled job + sample outputs | Not Started | 4.1 | 5 | Keep output format consistent (CSV/JSON); store in S3 prefix for reporting
4.3 | Define Feedback Loop Patterns (OPA Targets) | Define patterns that should generate preventive IaC policies (e.g., overly-permissive IAM, public S3, missing encryption). | Pattern catalog + mapping to OPA/controls | Not Started | 4.2 | 4 | Focus on high-signal patterns to avoid noisy policy generation
4.4 | Develop OPA Policy Generator | Implement generator that turns normalized findings into draft OPA/Rego policies with tests and metadata. | Rego templates, unit tests, policy metadata | Not Started | 4.3 | 12 | Keep generator deterministic; include safe defaults and explicit allowlists
4.5 | Automate PR Workflow for Policies | Automate: finding → analysis → policy generation → pull request to policies repo with CI checks and approvals. | End-to-end automation, PR creation, approval gates | Not Started | 4.4 | 8 | Use least-privilege GitHub token; require manual approval before merge
4.6 | Governance: Testing, Rollback, Exceptions | Define governance for generated policies: required tests, exception process, rollback plan, and audit trail. | Policy governance doc + CI checks + exception template | Not Started | 4.5 | 6 | Prevent breaking changes; maintain allowlist/denylist versioning
4.7 | Validate Policy Generation (5+ Policies) | Trigger representative violations and verify policy drafts are correct, minimal, and don’t block legitimate changes. | 5+ generated policies validated with tests | Not Started | 4.5 | 6 | Track false positives and add exception patterns
4.8 | Trend Dataset Readiness (7/30-day) | Validate the dataset supports trend reporting (7-day minimum now; 30-day collection plan documented). | Trend-ready dataset + validation notes | Not Started | 4.2 | 3 | Phase 5 will visualize these trends; ensure stable time windows
4.9 | Handoff to Visualization Phase | Finalize metric definitions, dataset locations, and documentation handoff to Phase 5 for dashboard/report buildout. | Handoff checklist completed | Not Started | 4.8 | 2 | Ensure links to datasets and query library are documented

## Phase 5 - Visualization & Docs
Phase 5: Visualization & Documentation (Weeks 17-20) - REPORTING
Task ID | Task Name | Description | Requirements | Status | Dependencies | Est Hours | Notes
5.1 | Define KPIs & Reporting Requirements | Define core security KPIs (MTTD/MTTR, coverage, cost) and reporting cadence; map KPIs to data sources. | KPI list, dashboard wireframes, data source mapping | Not Started |  | 3 | Align with Success Metrics sheet; define owners and review cadence
5.2 | Build Metrics Dataset & Queries | Create reusable queries/filters and calculations to produce a clean metrics dataset for dashboards and reports. | Query library, metric formulas, sample dataset | Not Started | 5.1 | 5 | Prefer simple sources first (Config compliance, CloudTrail events); automate exports where possible
5.3 | Create CloudWatch Dashboards (Ops Health) | Create dashboards for baseline health: CloudTrail status, Config recorder status, rule compliance overview, error signals. | Dashboards created, screenshots captured, runbook links | Not Started | 5.2 | 4 | Keep dashboards minimal and actionable; add links to docs
5.4 | Create Trend & Compliance Dashboards | Build visualizations for trends: 7/30-day compliance, top failing rules, MTTD/MTTR trendlines, cost trend (optional). | Trend dashboards with filters by env/time | Not Started | 5.3 | 6 | Grafana/QuickSight optional; document data sources and refresh rate
5.5 | Automated Reporting Pack | Create weekly/monthly report template (Markdown/PDF) summarizing KPIs, compliance, top findings, and recommendations. | Report template + automation script + sample outputs | Not Started | 5.4 | 4 | Include executive summary + appendix with raw tables
5.6 | Runbooks & Data Dictionary | Write operational documentation: deployment, verification, troubleshooting, and a data dictionary for all metrics/dashboards. | Runbooks complete, data dictionary published in repo | Not Started | 5.5 | 8 | Ensure docs are copy/paste friendly; include "known issues" section
5.7 | Architecture & Data Flow Diagrams | Produce final architecture and data-flow diagrams showing log generation, encryption, storage, evaluation, and reporting. | Diagrams (PNG/SVG) + source files | Not Started | 5.6 | 4 | Add diagrams to README and module docs
5.8 | Verification & Demo Guide (with Screenshots) | Create step-by-step verification and demo guide with screenshots (AWS Console + CLI) demonstrating end-to-end operation. | Demo script, verification checklist updates, screenshots | Not Started | 5.7 | 6 | Make it reproducible for an external reviewer
5.9 | Final Report & Appendices (Visualization-First) | Write final report emphasizing results, dashboards, metrics interpretation, and lessons learned. Compile appendices. | Final report, appendices, references | Not Started | 5.8 | 10 | Include KPI tables/figures sourced from dashboards
5.10 | Final Presentation & Narrative | Create final slide deck and narrative focused on security posture improvements, visuals, and live demo walkthrough. | Slide deck, speaker notes, demo plan | Not Started | 5.9 | 6 | Highlight CIS coverage, costs, and measurable outcomes

## Success Metrics
Project Success Criteria & Metrics
Metric Category | Metric | Target | Current | Status
Detection | MTTD (Mean Time to Detect) | <5 minutes | TBD | Not Measured
Remediation | MTTR (Mean Time to Remediate) | <5 minutes | TBD | Not Measured
Accuracy | False Positive Rate | <5% | TBD | Not Measured
Coverage | Detection Coverage (Critical) | 100% | TBD | Not Measured
Prevention | Pre-deployment Block Rate | >80% | TBD | Not Measured
Performance | IaC Scan Time (GitHub Actions) | <5 minutes | TBD | Not Measured
Operational | System Availability | >99% | TBD | Not Measured
Cost | Monthly AWS Infrastructure Cost | <€15 | €2.72 | On Track (18% of budget)
Feedback Loop | Auto-Generated OPA Policies | >5 policies | 0 | Not Started

## Attack Scenarios
10 Attack Scenarios for Testing (Phase 5)
ID | Scenario Name | Description | Detection Method | Remediation Method | Target Metric
S1 | Wildcard IAM Policy | Deploy wildcard (*) IAM policy via Terraform | AWS Config Rule + Security Hub | Lambda automatic removal | MTTD <5min, MTTR <5min
S2 | Overpermissive Role | Create IAM role with Admin-like permissions | Config Rule trigger | Lambda remediation with approval | MTTR <5min after approval
S3 | Unrotated Access Keys | Simulate IAM access keys >90 days old | Config compliance detection | Lambda auto-disable | Detection coverage
S4 | MFA Disabled | Disable MFA on IAM user account | Security Hub alert | Manual remediation + alert | MTTD <5min
S5 | External Account Access | Grant external account access to S3/IAM role | IAM Access Analyzer | Lambda remediation + approval | Analyzer detection
S6 | S3 Public Access | Make S3 bucket publicly accessible | Config Rule + Security Hub | Lambda auto-block public access | MTTR <5min
S7 | Assume Role Trust Policy | Create overly permissive AssumeRole trust policy | Custom Config Rule | Lambda policy restriction | Detection coverage
S8 | Inline Policy Violations | Attach inline policy with excessive permissions | Security Hub finding | Lambda policy removal | MTTD <5min
S9 | CloudTrail Logging Gaps | Disable CloudTrail in region | Config Rule monitoring | Lambda auto-re-enable | System health monitoring
S10 | Security Hub Integration | Test Security Hub aggregation failure | CloudWatch alarm | Manual verification + fix | System availability >99%

## Budget Tracker
Budget & Cost Tracking (Target: <€15/month)
Service | Monthly Cost (€) | Phase Introduced | Optimization Strategy | Notes
CloudTrail | 1.8 | Phase 1 | Single trail, management events only | DEPLOYED: Single multi-region trail, management events only
S3 Storage | 0.02 | Phase 1 | Lifecycle policies (30→90→180→365 days) | DEPLOYED: 2 buckets with lifecycle policies (30→90→180→365 days)
KMS Key | €0.90 | Phase 1 | Single CMK with auto-rotation | Required for encryption
AWS Config | €0.00 | Phase 1 | Free tier (first 1000 config items) | Stay under free tier
Security Hub | €0.00 | Phase 1 | Free for 30 days, then optimize | Monitor cost after trial
Lambda | €0.00 | Phase 2 | Free tier (1M requests/month) | Low invocation volume
EventBridge | €0.00 | Phase 2 | Free tier | Event routing
DynamoDB | €0.00 | Phase 2 | Free tier (25GB, 200M requests) | State tracking table
SNS | €0.00 | Phase 2 | Free tier (1000 emails) | Approval notifications
CloudWatch Logs | €0.45 | Phase 2 | Limited retention (7-14 days) | First 5GB free
GitHub Actions | €0.00 | Phase 3 | Free for public repos | 2000 minutes/month free
BridgeCrew API | €0.00 | Phase 3 | Free tier | Limited API calls
Grafana (EC2 t2.micro) | €0.00 | Phase 4 | Free tier eligible (750hr/month) | 12 months free tier
IAM Access Analyzer | €0.00 | All Phases | No additional cost | Included with account
TOTAL CURRENT (Phase 1)
BUDGET LIMIT (Monthly) | 15
REMAINING BUDGET
BILLING ALERTS CONFIGURED
Alert at €5 (33% budget)
Alert at €10 (67% budget)
Alert at €14 (93% budget - critical)
PHASE 1 ACTUAL SPEND ANALYSIS
Deployed Services | Monthly Cost (€) | Annual (€) | Status
KMS Key (1x CMK) | 0.9 |  | LIVE
S3 Storage (2x buckets) | 0.02 |  | LIVE
CloudTrail (multi-region) | 1.8 |  | LIVE
ACTUAL PHASE 1 TOTAL
Budget Remaining

## Technology Stack
IAM-Secure-Gate Technology Stack
Category | Technology | Purpose | Phase
AWS Services | CloudTrail | Audit logging for all IAM events | Phase 1
AWS Services | AWS Config | Compliance checking and config rules | Phase 1
AWS Services | IAM Access Analyzer | External access detection | Phase 1
AWS Services | Security Hub | Central security dashboard | Phase 1
AWS Services | EventBridge | Event routing to remediation | Phase 2
AWS Services | Lambda | Serverless remediation functions | Phase 2
AWS Services | SNS | Approval workflow notifications | Phase 2
AWS Services | DynamoDB | State tracking for remediations | Phase 2
AWS Services | S3 | Log storage with lifecycle policies | Phase 1
AWS Services | KMS | Encryption key management | Phase 1
AWS Services | CloudWatch | Metrics and logging | All Phases
IaC & Version Control | Terraform 1.5+ | Infrastructure as Code | All Phases
IaC & Version Control | Git | Version control | All Phases
IaC & Version Control | GitHub | Code repository and CI/CD | Phase 3
Security Tools | Checkov | 750+ IaC security policies | Phase 3
Security Tools | OPA (Open Policy Agent) | Custom policy engine | Phase 3-4
Security Tools | Conftest | Terraform plan validation | Phase 3
Security Tools | BridgeCrew API | Severity scoring and intelligence | Phase 3
CI/CD | GitHub Actions | PR security gate automation | Phase 3
Monitoring | Grafana | Metrics dashboards and visualization | Phase 4
Development | PowerShell 7+ | Automation scripts (Windows) | All Phases
Development | Python 3.9+ | Lambda function development | Phase 2-4
Development | boto3 (AWS SDK) | Python AWS API interactions | Phase 2-4
Development | AWS CLI | Command-line operations | All Phases
Development | Visual Studio Code | IDE for development | All Phases

## Risks & Mitigations
Risk Assessment & Mitigation Strategies
Risk | Impact | Mitigation | Contingency
AWS cost overrun | High - Could exceed budget | Billing alerts at €5/€10/€14, S3 lifecycle policies, Free Tier optimization | Reduce log retention to 7 days, use LocalStack for testing, request AWS credits
OPA/Rego learning curve | Medium - Skill gap could delay Phase 3 | Start Phase 3 in Week 7 (parallel with Phase 2), dedicated learning time, supervisor guidance | Use Checkov-only for Phase 3 MVP, defer custom OPA policies to Phase 4 stretch goal
API rate limits | Medium - GitHub/AWS throttling | Exponential backoff retry logic, intelligent caching, batch operations | Reduce EventBridge rule frequency, implement queue-based processing
Time constraints / scope creep | High - 20 weeks is tight | 2-week buffer built into timeline, weekly supervisor check-ins, strict MVP focus per phase | Descope to 3 core misconfiguration types, defer ML false-positive reduction to future work
AWS service availability | Low - Regional outages | Multi-region architecture design, CloudWatch alarms for service health | Local testing environment with mocked AWS services, documentation of workarounds

## Deployment Details
Current Deployment State (As of 2025-12-20)
Resource Type | Resource Name | Module | Status | Notes
Data Source | aws_caller_identity.current | root | DEPLOYED | Account information
Data Source | aws_region.current | root | DEPLOYED | Current region
KMS Key | aws_kms_key.logs | foundation | DEPLOYED | Customer-managed key with auto-rotation
KMS Alias | aws_kms_alias.logs | foundation | DEPLOYED | Alias for easy key reference
KMS Policy | aws_kms_key_policy.logs | foundation | DEPLOYED | Access control for KMS key
S3 Bucket | aws_s3_bucket.cloudtrail | foundation | DEPLOYED | CloudTrail log storage
S3 Bucket | aws_s3_bucket.config | foundation | DEPLOYED | AWS Config log storage (ready for Config)
S3 Encryption | cloudtrail SSE-KMS | foundation | DEPLOYED | Server-side encryption with KMS
S3 Encryption | config SSE-KMS | foundation | DEPLOYED | Server-side encryption with KMS
S3 Versioning | cloudtrail versioning | foundation | DEPLOYED | Version control for log integrity
S3 Versioning | config versioning | foundation | DEPLOYED | Version control for log integrity
S3 Lifecycle | cloudtrail lifecycle | foundation | DEPLOYED | Cost optimization (30→90→180→365 days)
S3 Lifecycle | config lifecycle | foundation | DEPLOYED | Cost optimization (30→90→180→365 days)
S3 Security | cloudtrail public access block | foundation | DEPLOYED | 4-layer public access blocking
S3 Security | config public access block | foundation | DEPLOYED | 4-layer public access blocking
S3 Policy | cloudtrail bucket policy | foundation | DEPLOYED | Bucket access control
S3 Policy | config bucket policy | foundation | DEPLOYED | Bucket access control
S3 Ownership | cloudtrail ownership controls | foundation | DEPLOYED | Bucket owner enforcement
S3 Ownership | config ownership controls | foundation | DEPLOYED | Bucket owner enforcement
CloudTrail | aws_cloudtrail.main | cloudtrail | DEPLOYED | Multi-region trail capturing IAM events
TOTAL DEPLOYED RESOURCES: | 20
PENDING DEPLOYMENT (Phase 1):
AWS Config | aws_config_configuration_recorder | config | NOT DEPLOYED | Required for compliance checking
AWS Config | aws_config_delivery_channel | config | NOT DEPLOYED | Delivers config snapshots to S3
AWS Config | aws_iam_role (Config) | config | NOT DEPLOYED | Service role for Config
AWS Config | aws_config_config_rule (5+ rules) | config | NOT DEPLOYED | CIS benchmark compliance rules
IAM Analyzer | aws_accessanalyzer_analyzer | access-analyzer | NOT DEPLOYED | External access detection
Security Hub | aws_securityhub_account | security-hub | NOT DEPLOYED | Security aggregation service
Security Hub | aws_securityhub_standards_subscription | security-hub | NOT DEPLOYED | CIS AWS Foundations Benchmark

## Next Steps
Immediate Next Steps to Complete Phase 1
Priority | Task | Action Items | Est. Hours
1 - HIGH | Deploy AWS Config Service | 1. Create IAM role for Config 2. Create Config recorder 3. Create delivery channel 4. Start recorder 5. Test with terraform apply | 3 hours
2 - HIGH | Deploy AWS Config Rules (5+) | 1. root-account-mfa-enabled 2. iam-password-policy 3. access-keys-rotated 4. iam-user-mfa-enabled 5. cloudtrail-enabled 6. Test rule evaluation | 3 hours
3 - MEDIUM | Deploy IAM Access Analyzer | 1. Create analyzer resource 2. Configure for account scope 3. Verify findings generation 4. Test with external access scenario | 2 hours
4 - MEDIUM | Deploy Security Hub | 1. Enable Security Hub 2. Enable CIS AWS Foundations Benchmark 3. Integrate with Config 4. Integrate with IAM Access Analyzer 5. Review initial findings | 4 hours
5 - MEDIUM | Execute 3 Test Scenarios | 1. Wildcard IAM policy test 2. MFA disable test 3. External access test 4. Measure MTTD for each 5. Document results | 4 hours
6 - LOW | Complete Phase 1 Documentation | 1. Finish README.md 2. Create architecture diagram 3. Document all deployed resources 4. Add troubleshooting guide 5. Update DEPLOYMENT-LOG.md | 5 hours
TOTAL REMAINING EFFORT: |  |  | 21 hours
ESTIMATED COMPLETION: |  | End of Week 4 | (On Schedule ✓)